## Slide 1: MSc Project – TaylorFlow
Matthew Woods
Supervisor – Vivien Raymond

## Slide 2: Overall Objective
Produce TaylorF2 Waveform in an architecture (TensorFlow) that enables GPU parallelisation.
This will result in a significant speed increase in the execution of thye code and will allow faster detection times.

## Slide 3: Benefits of faster detections and parameter fitting
More expansive parameter fitting
  Able to fit ‘sub threshold’ events and build statistical argument for astrophysical events
Better detection Follow-up
  Fast and confident detections enable rapid EM follow up searches, improving localisation.
  Easier follow up as detection rates increase with sensitivity.

## Slide 4: Project Objectives
Familiarisation with TensorFlow
Produce TaylorF2 approximant in TensorFlow Architecture
  Start at 0PN and increase to 3.5PN
  Compare against existing versions (pyCBC etc.)
Produce Inner Product and SNR equation in TensorFlow Architecture
  Compare against results from LIGO data
Increase speed of computation with GPU implementation
  Evaluate speed increase in comparison with other taylorF2 models

## Slide 5: Objectives - Familiarisation with TensorFlow
Numerous Tutorials available online
Focusing on Non- Machine learning example on TensorFlow
  Mandelbrot set
  Partial Differential equations
  0PN waveform
Timescale - 1 week for a working knowledge, with learning expanding throughout project

## Slide 6: Objectives - Producing Waveform Model
Producing TaylorF2 model with no spin, eccentricity, or tidal effects
Will produce 0PN through to 3.5PN waveforms
Aim to implement 0.5PN waveforms every 1-2 weeks, however complexity increases at high PN orders

## Slide 7: Objectives - Producing Overlap Equation
Producing equation to compare waveforms with data or other waveforms
Requires LIGO data (PSD data etc.)
Will take around two weeks to develop

## Slide 8: Objectives – GPU Implementation
TensorFlow enables simple porting of tasks to multiple GPUs
Speed increase will be compared to other TaylorF2 models in previously developed packages
Risks include TensorFlow waveform not maximising use of GPU, slowing progress

## Slide 9: Timeline